## REN EN status 2022
Status of commitments defined under act4nature Portugal ¦ 2020-2022 |  |  |  | Relation to common commitments | [9 empty] | Status |  |  | Report/communication
Individual commitments | Scope | Monitoring indicators | Implementation timeline | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Commitment status | Implementation status | Observations | Communication | Support | Report on the implementation of commitments
Developing a strategic plan for integrating biodiversity into the company's activities | REN Group | Strategic plan for integrating biodiversity into the company's activities published on the company's website | 2020-2022 | [10 empty] | Concluded | 100% | Strategy defined in 2022. | Communicated | Integrated Report 2022 (Natural Capital Chapter) | This document | bar: Relation to common commitments 1
Integrating task forces (TF), work groups (WG) or other equivalent within the scope of biodiversity and ecosystem services | REN Group | Participation in TF/WG/other equivalent | 2020-2021 | [10 empty] | Concluded | 100% | With the support of CIBIO, during 2021, REN participated on CIGRE’s Working Group C3.16 “Wildlife and electrical infrastructure”. The working group submitted a Technical Brochure as a result to CIGRE, which is under evaluation by that entity. | Communicated | https://e-cigre.org/publication/876-interactions-between-electrical-infrastructure-and-wildlife | This document | bar: Relation to common commitments 4; Relation to common commitments 7; Relation to common commitments 9
Establishing local, regional or global partnerships in projects that have a significant impact on biodiversity (e.g., LIFE) to solve specific problems in line with the company's strategic plan | REN Group | Partnerships and corresponding results | 2020-2022 | [10 empty] | Concluded | 100% | REN has been developing a number of partnerships in this area. We highlight the participation in Life Maronesa, in Vila Pouca de Aguiar, and the protocol, in the final phase of development, to support native animal species that adopt extensive grazing as tool to reduce the risk of fire (vegetation management) in rural areas, thus contributing to the preservation of these species and to the enhancement of the territory. In march 2022, REN joined the Transnational Strategy to fight Cortaderia selloana, through REN - Rede Elétrica Nacional, SA, as the electricity transmission concessionaire and REN Gasodutos, SA, as the gas transmission concessionaire. This transnational strategy was born under the LIFE Stop Cortaderia Project. | Communicated | https://www.ren.pt/en-gb/media/news/garrano-horses-will-help-prevent-fires-on-cabreira-mountain | This document | bar: Relation to common commitments 4; Relation to common commitments 9
Carrying out/collaborating in sectorial actions to raise awareness regarding Biodiversity, sharing knowledge and good practices adopted | Grupo REN | Carried out and promoted sectorial actions in the area of biodiversity | 2020-2022 | [10 empty] | Concluded | 100% | Workshops with internal and external stakeholders to define a biodiversity strategy. Promotion of initiatives such as "Citizens Science", in partnership with CIBIO. Publication of the biodiversity strategy. | Communicated | Integrated Report 2022 | This document | bar: Relation to common commitments 1 to Relation to common commitments 4; Relation to common commitments 9
Considering the development of an easement-corridor management document to maximise biodiversity and ecosystem services | Grupo REN | Published guidelines for ecological management and good practices Good practices implemented | 2020-2022 | [10 empty] | Ongoing | 50% | With the support of CIBIO, REN contracted the University of Évora to carry out a study to diagnose the biodiversity values present in our rights-of-way. | Not communicated |  | This document | bar: Relation to common commitments 6 to Relation to common commitments 7; Relation to common commitments 9
Identifying the bird species most affected by collisions with REN's lines | REN Group | Report and scientific communications | 2020-2022 | [10 empty] | Concluded | 100% | All records of bird collisions with REN lines between 2003 and 2015 were compiled. Preliminary results were presented at the IENE 2020 International Conference, "LIFE LINES - Linear Infrastructure Networks with Ecological Solutions" (held online between 12-14 January 2021). | Comunicado | IENE International Conference 2020 | This document | bar: Relation to common commitments 9
Carrying out an inventory of the biodiversity present in the supports and in the easement corridors | REN Group | Results of the inventory published | 2020-2022 | [10 empty] | Concluded | 100% | Between January and May 2021, field investigations were carried out to identify which bird species use REN's supports as nesting sites in southern Portugal (Report with preliminary results published in June 2021). During the fieldwork, particular attention was paid to surveying poles potentially used by endangered species. A second year of research will take place between January and May 2022 and will cover the north and centre of Portugal. The results will then be integrated with those of 2021 and published. REN and the University of Évora signed a protocol in 2021 for the study and conservation of animal communities under power transmission lines. This partnership is part of the LIFE LINES project - "Linear Infrastructure Networks with Ecological Solutions" and allows for the creation of real "biodiversity islands" under the supports. | Communicated | Integrated Report 2022 (Natural Capital Chapter) | This document | bar: Relation to common commitments 3; Relation to common commitments 9
Establishing a partnership with CIBO-University of Porto to continue the collaboration initiated in 2015, within the scope of the REN Chair on Biodiversity, seeking to implement a programme of biodiversity research and mitigation of impacts generated by the company | REN Group | Investment in ES&B research programmes (to be integrated in the calculation of the indicator: investment in ES&B/GVA) | 2020-2022 | [10 empty] | Concluded | 100% | In 2020, a new protocol was established between REN and the Centre for Research in Biodiversity and Genetic Resources (CIBIO-InBIO) for the years 2020-2023. | Communicated | Integrated Report 2022 (Natural Capital Chapter) | This document | bar: Relation to common commitments 3; Relation to common commitments 9
Ensuring the monitoring or participation of entity/entities and/or specialist(s) in ecology, biology or related sciences, in projects in which their involvement is deemed necessary and an added value to defining and implementing actions that contribute to reducing or mitigating impacts | REN Group | Projects carried out with teams specialised in ecology, biology or related sciences and their results | Ongoing | [10 empty] | Concluded | 100% | The monitoring or participation of entity(ies) and/or specialist(s) in ecology, biology or related sciences is a common practice included in REN’s value chain. | Not communicated |  | This document | bar: Relation to common commitments 9
Investing in the creation of ecological corridors where they are ecologically relevant and within the scope of the infrastructure managed by the company | REN Group | Investment in ecological corridors/total investment in nature conservation | 2020-2022 | [10 empty] | Ongoing | 25% | In 2020, in the municipality of Penacova, REN implemented a project for the reforestation of rights-of-way, which consisted of removing eucalyptus and acacias from a corridor of around 130 ha and replacing them with strawberry trees. In 2022, the same methodology was applied to a corridor of about 60 ha in the municipality of Albergaria-a-Velha. The development of guidelines for biodiversity management in rights of way is planned to begin in 2023. | Not communicated |  | This document | bar: Relation to common commitments 6
Participating in public consultations related to and impacting biodiversity and ecosystem services (e.g., National Strategy for Nature Conservation and Biodiversity) | REN Group | Public consultations in which the company participates | Ongoing | [10 empty] | Concluded | 100% | Participation in public consultations on issues that concern us is part of our governance model. | Not communicated |  | This document
Implementing compensatory measures in situations where the impacts cannot be minimised | REN Group | Area (ha) and/or Investment (euros) of the implemented compensation measures | Ongoing | [10 empty] | Concluded | 100% | An area of 3.922 hectares was executed between 2010 and 2022, of which 278 in 2022. | Communicated | Integrated Report 2022 (Natural Capital Chapter) | This document | bar: Relation to common commitments 5
Raising employee awareness, namely by raising awareness about the importance of biodiversity and ecosystem services | REN Group | Number of employees who participated in awareness-raising activities | 2020-2022 | [10 empty] | Concluded | 100% | In 2020, about 42 REN employees participated in the Biodiversity Chair Symposium. | Communicated | Annual Report 2021 | This document | bar: Relation to common commitments 8
Promoting employee knowledge, through their participation in environmental volunteering activities or in carrying out local biodiversity inventories | REN Group | Number of employees who participated in environmental volunteering activities | 2020-2022 | [10 empty] | Not started | 0% | No on-site volunteering initiatives took place in 2022 (as a result of Covid-19 restrictions). | Not communicated |  | This document | bar: Relation to common commitments 8
Training employees in good environmental practices to be applied in the company's operations, specifying the contribution to biodiversity | REN Group | Percentage of employees trained in good environmental practices | 2020-2022 | [10 empty] | Concluded | 50% | In 2022, 4,567 hours of training in quality, environment and safety were carried out. As part of the commitments to reduce GHG emissions, awareness-raising sessions have been held to publicise the initiatives underway, involving all of REN's operational areas. In 2023, 2 internal webinars on sustainability will be held at REN. | Communicated | Integrated Report 2022 (Natural Capital Chapter) | This document | bar: Relation to common commitments 8
Fostering the development and implementation of initiatives by employees in favour of biodiversity | REN Group | Number of employees who participated in biodiversity initiatives | 2020-2022 | [10 empty] | Concluded | 0% | No on-site initiatives took place in 2022 (as a result of Covid-19 restrictions). | Not communicated |  | This document | bar: Relation to common commitments 8
Investing in projects of scientific entities or other stakeholders that seek nature conservation | REN Group | Investment in projects of scientific entities for nature conservation (to be integrated in the calculation of the indicator: investment in ES&B/GVA) | 2020-2022 | [10 empty] | Concluded | 100% | Between 2020 and 2021, REN invested around 370 thousand euros in nature conservation projects (REN Chair in Biodiversity, Bird Nesting, etc.). | Not communicated |  | This document | bar: Relation to common commitments 9
Reporting, annually, in the clearest and most transparent manner possible, the progress in meeting individual commitments | REN Group | Section for reporting on the evolution of act4nature commitments in the annual sustainability report | Ongoing | [10 empty] | Concluded | 100% | This table, which is published on REN’s website. | Communicated | This document | This document | bar: Relation to common commitments 10